## Sheet1
BUG REPORT of Distributor Dashboard
Bug ID | Module | Severity | Priority | Summary | Steps to Reproduce | Expected Result | Actual Result
BUG-001 | Distributor Dashboard | Minor | P2 | KPI cards on Distributor Dashboard have no hover effect | 1. Login as Distributor user 2. Navigate to /distributor/dashboard.php 3. Hover mouse over any KPI card (STOCK ON HAND, ACTIVE SALESMEN, PENDING APPROVALS, DUE TO WAREHOUSE, OUTSTANDING BALANCE, ORDERS THIS MONTH, LAST ORDER STATUS) | Cursor changes to pointer on hover; card shows visual feedback (shadow effect, color change, or scale animation) indicating interactivity | No hover effect on any KPI card. Cursor remains default arrow. No visual feedback (shadow, color change, scale, or border change) when hovering. Cards appear completely static despite being clickable.
BUG-002 | Distributor Dashboard | Major | P1 | Customer Orders Trend chart missing blue "Orders" line | 1. Login as Distributor user 2. Navigate to /distributor/dashboard.php 3. View "Customer orders trend" chart | Chart displays both data series: "Orders" as blue line and "Sales (PKR)" as green line/bar. Both series should be visible with proper legend | Blue "Orders" line is completely missing from the chart. Only green "Sales (PKR)" series is visible. Legend shows both but blue line is not rendered on the chart. X-axis shows months (Feb 2026 - Jul 2026) but no blue data points or line.
BUG-003 | My Sales Team | Critical | P0 | Delete button for salesman does not work / no action on click | 1. Login as Distributor user 2. Navigate to /distributor/sales_team.php 3. Locate a salesman in the table (e.g., Ahmed Khan) 4. Click the "Delete" button in the ACTION column | Delete confirmation dialog appears; upon confirmation, salesman is deleted (or appropriate constraint message shown) | Delete button does nothing when clicked. No confirmation dialog appears. No error message shown. No action occurs. Salesman remains in list.
BUG-004 | Sales Team Orders | Minor | P2 | Month filter placeholder "mm/dd/yy" is not responsive on Sales Team Orders page | 1. Login to the application 2. Click "Sales Team Orders" from sidebar 3. Observe the date filters "From" and "To" fields in the filter section 4. Resize browser window to tablet/mobile size | Date filter placeholders should resize and adapt properly, remaining fully visible and usable on all screen sizes | Date filter placeholders "mm/dd/yy" are not responsive; they cut off or become misaligned on smaller screens
BUG-005 | "+ Add salesman" button appears twice on the page (duplication) | Minor | P2 | My Sales Team page - "+ Add salesman" button appears twice (duplication) | 1. Login to the application 2. Click "My Sales Team" from the sidebar 3. Observe the page for "+ Add salesman" buttons | Only one "+ Add salesman" button should be displayed on the page | Two "+ Add salesman" buttons are displayed on the page (duplication issue)
BUG-006 | Payment Methods | Critical | P0 | Payment Methods accepts emojis/special characters in Method name field | 1. Login to the application 2. Click "Payment Methods" from sidebar 3. Enter emojis (😊😊😊😊😊😊😊😊😊😊😊) in Method name field 4. Click "Add method" | Only valid characters (letters, numbers, spaces) should be allowed; emojis/special characters should be restricted or validation error displayed | Emojis/special characters are accepted and added to Configured methods table
BUG-007 | Account Ledger | Critical | P1 | Customer payment of PKR 300 is recorded in system but not displayed in Customer Payment Receipts on Account Ledger page | 1. Login to the application 2. Navigate to Receive Salesman Payment page 3. Record a payment of PKR 300 from salesman (Ahmed Khan) 4. Navigate to Account Ledger page 5. Observe "Customer payment receipts" section | Customer payment receipt of PKR 300 should be displayed in Customer Payment Receipts section with receipt details (RECEIPT #, DATE, SALESMAN, AMOUNT, etc.) | Customer Payment Receipts section shows "No customer payment receipts yet." or "0 receipts" despite PKR 300 payment being recorded successfully in the system
BUG-008 | Reports | Major | P1 | Financial Position (Period) block and its cards (Receivable, Payable, Net) are not clickable/navigable on Reports page | 1. Login to the application 2. Click "Reports" from sidebar 3. Scroll to "Financial position (period)" section 4. Click on the section header or any card (Receivable: PKR 0, Payable: PKR 500, Net: PKR -500) | User should be able to click/navigate to detailed financial position report showing Receivable, Payable, and Net breakdown | Financial Position section and cards are not clickable; no navigation occurs; appears as static text only
BUG-009 | Reports | Medium | P2 | No reset/clear button available to remove date filter on Reports page | 1. Login to the application 2. Click "Reports" from sidebar 3. Select From date and To date 4. Click "Run report" 5. Observe filter section for reset/clear option | User should have a "Reset" or "Clear" button to remove applied date filters and view all data | No reset/clear button is available; user cannot remove applied date filters once set
BUG-010 | Audits | Critical | P0 | Audit Trail only shows Login/Logout events (Auth events), not recording order, delivery, or payment activities | 1. Login to the application 2. Place a customer order on 01 Jul 2026 3. Deliver the order on 01 Jul 2026 4. Record payment of PKR 300 on 03 Jul 2026 5. Navigate to Audits page 6. Search for these activities | All user activities should be logged in Audit Trail including: Order placed, Order delivered, Payment received, Stock issued, Stock received, etc. | Audit Trail only displays authentication events (login/logout). No audit records found for orders placed, deliveries, or payments. Only AUTH EVENTS are being recorded (10 logs).
BUG-011 | Receive Salesman Payment | Medium | P1 | Receive Salesman Payment page - Payment Receipts table is not responsive and displays distorted/garbled data | 1. Login to the application 2. Navigate to Receive Salesman Payment page 3. Resize browser to tablet or mobile view 4. Observe Payment Receipts table | Payment Receipts table should resize properly with horizontal scroll or stacked view, displaying clean data on all screen sizes | Table displays distorted/garbled data with letters "S A L E S M A N - P A Y - 2 0 2 6 0 7 0 1 1 6" split vertically and "BAKTEPT / RAQESHTAN" instead of proper column headers (Receipt, Date, Salesman, Request, Method, Amount) - UI rendering issue